## Foxhall Components
181
Parking Garage | 1.01 | Concrete repairs, B1 level | 1 | AL | 50000 | 50000 | 2011 | 12 | 5 | 2023 | 4167
Parking Garage | 1.02 | Vehicle traffic coating B1 level, first time | 23000 | SF | 6 | 138000 | - | one_time_project | 5 | 2023 | $-
Parking Garage | 1.03 | Vehicle traffic coating, B1 level, recoat | 23000 | SF | 4 | 92000 | - | 12 | 17 | 2035 | 7667
Parking Garage | 1.04 | Concrete repairs, B2 level | 1 | AL | 40000 | 40000 | 2011 | 20 | 13 | 2031 | 2000
Parking Garage | 1.05 | Vehicle traffic coating B2 level, first time | 18000 | SF | 6 | 108000 | - | one_time_project | 6 | 2024 | $-
Parking Garage | 1.06 | Vehicle traffic coating, B2 level, recoat | 18000 | SF | 4 | 72000 | - | 12 | 18 | 2036 | 6000
Parking Garage | 1.07 | Paint garage | 1 | LS | 80000 | 80000 | - | 20 | 6 | 2024 | 4000
Parking Garage | 1.08 | Garage door replacement | 2 | EA | 15000 | 30000 | - | 15 | 5 | 2023 | 2000
Parking Garage | 1.09 | Garage door repair allowance | 1 | AL | 5000 | 5000 | - | 5 | 10 | 2028 | 1000
Parking Garage | 1.1 | Loading dock doors replacement | 1 | LS | 15000 | 15000 | - | 15 | 4 | 2022 | 1000
Parking Garage | 1.11 | Garage railings | 1 | AL | 5000 | 5000 | - | 40 | 6 | 2024 | 125
Parking Garage | 1.12 | Garage exhaust fans | 1 | AL | 5000 | 5000 | - | 10 | 5 | 2023 | 500
Parking Garage | 1.13 | Wall leak repair allowance | 1 | AL | 6000 | 6000 | - | 10 | 1 | 2019 | 600
Parking Garage | 1.14 | Garage expansion joint seal | 80 | LF | 200 | 16000 | - | 15 | 5 | 2023 | 1067
Parking Garage | 1.15 | Garage steel beams and fireproofing | 1 | AL | 10000 | 10000 | 1972 | 55 | 6 | 2024 | 182
Site Features | 2.01 | Gate house exterior refurbish | 1 | AL | 15000 | 15000 | - | 20 | 6 | 2024 | 750
Site Features | 2.02 | Gate house interior refurbish | 1 | AL | 15000 | 15000 | - | 20 | 6 | 2024 | 750
Site Features | 2.03 | Board room building exterior repairs | 1 | AL | 80000 | 80000 | - | 20 | 4 | 2022 | 4000
Site Features | 2.04 | Board room building interior refurbish | 1 | AL | 50000 | 50000 | - | 20 | 4 | 2022 | 2500
Site Features | 2.05 | Water feature pump and filter | 1 | LS | 5000 | 5000 | - | 15 | 3 | 2021 | 333
Site Features | 2.06 | Water feature piping | 1 | AL | 30000 | 30000 | 1972 | 55 | 9 | 2027 | 545
Site Features | 2.07 | Upper basin wall and basin repairs | 1 | AL | 7500 | 7500 | - | 10 | 6 | 2024 | 750
Site Features | 2.08 | Upper basin coating | 1000 | SF | 5 | 5000 | 2014 | 10 | 6 | 2024 | 500
Site Features | 2.09 | Stone wall repairs | 1 | AL | 25000 | 25000 | - | 10 | 1 | 2019 | 2500
Site Features | 2.1 | Reflecting pool basin repairs | 1 | AL | 10000 | 10000 | - | 10 | 6 | 2024 | 1000
Site Features | 2.11 | Reflecting pool basin coating | 10000 | SF | 5 | 50000 | 2014 | 10 | 6 | 2024 | 5000
Site Features | 2.12 | Tennis court fence | 400 | LF | 50 | 20000 | - | 40 | 14 | 2032 | 500
Site Features | 2.13 | Tennis court nets and wind screens | 1 | LS | 5000 | 5000 | - | 15 | 10 | 2028 | 333
Site Features | 2.14 | Tennis court resurfacing | 1 | LS | 35000 | 35000 | 2013 | 15 | 10 | 2028 | 2333
Site Features | 2.15 | Tennis court reconstruction | 1 | LS | 150000 | 150000 | 1972 | 60 | 14 | 2032 | 2500
Site Features | 2.16 | Property perimeter fence | 200 | LF | 50 | 10000 | 1972 | 55 | 9 | 2027 | 182
Site Features | 2.17 | Signage and site fixtures | 1 | AL | 10000 | 10000 | - | 20 | 6 | 2024 | 500
Site Features | 2.18 | Drainage improvement allowance | 1 | AL | 25000 | 25000 | - | 20 | 8 | 2026 | 1250
Site Features | 2.19 | Tree maintenance and repair allowance | 1 | AL | 30000 | 30000 | - | 20 | 3 | 2021 | 1500
Site Features | 2.2 | Landscape restoration allowance | 1 | AL | 30000 | 30000 | - | 20 | 4 | 2022 | 1500
Site Features | 2.21 | Irrigation allowance | 1 | AL | 15000 | 15000 | 2012 | 15 | 9 | 2027 | 1000
Site Features | 2.22 | Handrails | 1 | AL | 10000 | 10000 | - | 10 | 8 | 2026 | 1000
Site Features | 2.23 | Sidewalk replacement | 1 | AL | 25000 | 25000 | - | 10 | 3 | 2021 | 2500
Site Features | 2.24 | Front asphalt pavement sealing | 2600 | SY | 3 | 7800 | 2016 | 6 | 4 | 2022 | 1300
Site Features | 2.25 | Service area asphalt pavement sealing | 850 | SY | 3 | 2550 | 2016 | 6 | 4 | 2022 | 425
Site Features | 2.26 | Front asphalt milling and repaving | 2600 | SY | 25 | 65000 | - | 24 | 16 | 2034 | 2708
Site Features | 2.27 | Service area asphalt milling and repaving | 850 | SY | 25 | 21250 | - | 24 | 16 | 2034 | 885
Site Features | 2.28 | Curb and gutter replacement allowance | 1 | AL | 25000 | 25000 | - | 24 | 16 | 2034 | 1042
Site Features | 2.29 | Trench drains | 1 | AL | 25000 | 25000 | - | 20 | 16 | 2034 | 1250
Site Features | 2.3 | Site master plan | 1 | AL | 5000 | 5000 | - | 20 | 2 | 2020 | 250
Site Features | 2.31 | Stormwater system repair allowance | 1 | AL | 40000 | 40000 | - | 15 | 10 | 2028 | 2667
Site Features | 2.32 | Storage shed | 1 | AL | 20000 | 20000 | - | 30 | 2 | 2020 | 667
Pool Facilities | 3.01 | Whitecoat pool | 1 | LS | 10000 | 10000 | 2018 | 8 | 8 | 2026 | 1250
Pool Facilities | 3.02 | Tile and coping | 150 | LF | 80 | 12000 | 2018 | 25 | 25 | 2043 | 480
Pool Facilities | 3.03 | Pool deck coating | 3000 | SF | 5 | 15000 | 2018 | 10 | 10 | 2028 | 1500
Pool Facilities | 3.04 | Pool pump and filters | 1 | LS | 5000 | 5000 | 2018 | 15 | 15 | 2033 | 333
Pool Facilities | 3.05 | Pool piping | 1 | LS | 30000 | 30000 | - | 50 | 20 | 2038 | 600
Pool Facilities | 3.06 | Redecorate pool area | 1 | AL | 10000 | 10000 | 2018 | 12 | 12 | 2030 | 833
Pool Facilities | 3.07 | Pool heat exchanger | 1 | EA | 10000 | 10000 | - | 35 | 7 | 2025 | 286
Pool Facilities | 3.08 | Pool furniture allowance | 1 | AL | 8000 | 8000 | 2018 | 8 | 8 | 2026 | 1000
Pool Facilities | 3.09 | Pool deck replacement | 3000 | SF | 25 | 75000 | 2018 | 30 | 20 | 2038 | 2500
Pool Facilities | 3.1 | Pool fittings and fixtures | 1 | LS | 20000 | 20000 | 2018 | 30 | 20 | 2038 | 667
Pool Facilities | 3.11 | Pool doors and windows | 1 | LS | 80000 | 80000 | 1972 | 50 | 4 | 2022 | 1600
Pool Facilities | 3.12 | Pool area lighting | 1 | LS | 25000 | 25000 | 2018 | 15 | 15 | 2033 | 1667
Roofing | 4.01 | Gate house roof | 1 | LS | 6000 | 6000 | 1972 | 50 | 4 | 2022 | 120
Roofing | 4.02 | Board room building roof | 3000 | SF | 15 | 45000 | 2011 | 20 | 13 | 2031 | 2250
Roofing | 4.03 | Main roof replacement | 28000 | SF | 35 | 980000 | 1990 | 35 | 7 | 2025 | 28000
Roofing | 4.04 | Main roof repairs | 1 | AL | 10000 | 10000 | - | 10 | 17 | 2035 | 1000
Roofing | 4.05 | Roof expansion joint | 80 | LF | 70 | 5600 | - | 15 | 7 | 2025 | 373
Roofing | 4.06 | Cooling tower roof replacement | 1200 | SF | 40 | 48000 | 1990 | 25 | 7 | 2025 | 1920
Roofing | 4.07 | Cooling tower roof repairs | 1 | AL | 3000 | 3000 | - | 10 | 1 | 2019 | 300
Roofing | 4.08 | West stairway roof replacement | 1200 | SF | 30 | 36000 | 1990 | 35 | 7 | 2025 | 1029
Roofing | 4.09 | West stairway roof repairs | 1 | AL | 2000 | 2000 | - | 15 | 17 | 2035 | 133
Roofing | 4.1 | Roof fall protection | 1 | AL | 20000 | 20000 | - | 15 | 1 | 2019 | 1333
Roofing | 4.11 | Roof anchors | 1 | LS | 250000 | 250000 | - | 35 | 7 | 2025 | 7143
Roofing | 4.12 | Entrance canopy roof | 1000 | SF | 20 | 20000 | - | 20 | 12 | 2030 | 1000
Roofing | 4.13 | Roof over pool area | 1 | LS | 8000 | 8000 | 1972 | 50 | 4 | 2022 | 160
Roofing | 4.14 | Waterfall equipment room roof | 1 | LS | 10000 | 10000 | - | 30 | 6 | 2024 | 333
Building Exterior | 5.01 | Exterior maintenance program | 1 | LS | 600000 | 600000 | - | one_time_project | 2 | 2020 | $-
Building Exterior | 5.02 | Replace exterior caulk | 55000 | LF | 7 | 385000 | - | 15 | 11 | 2029 | 25667
Building Exterior | 5.03 | Clean exterior walls | 1 | LS | 300000 | 300000 | - | 15 | 11 | 2029 | 20000
Building Exterior | 5.04 | Concrete repair allowance | 1 | AL | 300000 | 300000 | - | 15 | 11 | 2029 | 20000
Building Exterior | 5.05 | Recoat balcony and terrace decks | 65000 | SF | 8 | 520000 | - | 15 | 11 | 2029 | 34667
Building Exterior | 5.06 | Repair and paint balcony ceilings | 65000 | SF | 5 | 325000 | - | 15 | 11 | 2029 | 21667
Building Exterior | 5.07 | Stucco repair allowance | 1 | AL | 50000 | 50000 | - | 15 | 11 | 2029 | 3333
Building Exterior | 5.08 | Brick pointing allowance | 1 | AL | 50000 | 50000 | - | 15 | 11 | 2029 | 3333
Building Exterior | 5.09 | Paint balcony railings | 1 | LS | 400000 | 400000 | - | one_time_project | 2 | 2020 | $-
Building Exterior | 5.1 | Replace balcony railings | 5500 | LF | 200 | 1100000 | 1972 | 55 | 21 | 2039 | 20000
Building Exterior | 5.11 | Replace residential windows and doors | 47000 | SF | 70 | 3290000 | 1972 | 55 | 21 | 2039 | 59818
Building Exterior | 5.12 | Replace curtainwall at elevator lobbies | 2800 | SF | 85 | 238000 | 1972 | 55 | 11 | 2029 | 4327
Building Exterior | 5.13 | Replace other windows | 600 | SF | 75 | 45000 | 1972 | 55 | 11 | 2029 | 818
Building Exterior | 5.14 | Replace main lobby doors and windows | 1 | LS | 60000 | 60000 | 1972 | 55 | 11 | 2029 | 1091
Building Exterior | 5.15 | Stone walls at main entrance | 1 | AL | 50000 | 50000 | - | 20 | 7 | 2025 | 2500
Building Exterior | 5.16 | Entrance canopy soffit | 1 | AL | 20000 | 20000 | - | 15 | 7 | 2025 | 1333
Building Exterior | 5.17 | Terrace soffits | 1 | AL | 30000 | 30000 | - | 15 | 21 | 2039 | 2000
Building Exterior | 5.18 | Paint exterior concrete | 1 | LS | 50000 | 50000 | - | 15 | 21 | 2039 | 3333
Building Exterior | 5.19 | Post tensioned concrete repair allowance | 1 | AL | 40000 | 40000 | - | 15 | 21 | 2039 | 2667
Building Exterior | 5.2 | Cooling tower screen walls | 1 | AL | 20000 | 20000 | 1972 | 40 | 6 | 2024 | 500
Mechanical Systems | 6.01 | Refurbish cooling towers | 1 | AL | 65000 | 65000 | - | 30 | 48 | 2066 | 2167
Mechanical Systems | 6.02 | Replace cooling towers | 2 | EA | 150000 | 300000 | 2006 | 30 | 18 | 2036 | 10000
Mechanical Systems | 6.03 | Refurbish chillers | 1 | AL | 30000 | 30000 | - | 30 | 36 | 2054 | 1000
Mechanical Systems | 6.04 | Replace chillers | 2 | EA | 250000 | 500000 | 1994 | 30 | 6 | 2024 | 16667
Mechanical Systems | 6.05 | Refurbish boilers | 1 | AL | 30000 | 30000 | - | 15 | 18 | 2036 | 2000
Mechanical Systems | 6.06 | Replace boilers | 2 | EA | 550000 | 1100000 | 1972 | 30 | 3 | 2021 | 36667
Mechanical Systems | 6.07 | Heat exchanger 1 - basement areas | 1 | EA | 35000 | 35000 | 1972 | 30 | 4 | 2022 | 1167
Mechanical Systems | 6.08 | Heat exchanger 2 - residential FCUs | 1 | EA | 50000 | 50000 | 1972 | 30 | 5 | 2023 | 1667
Mechanical Systems | 6.09 | Heat exchanger 3 - domestic hot water | 0 | EA | 35000 | 35000 | 1972 | - | - | - | $-
Mechanical Systems | 6.1 | Heat exchanger 4 - swimming pool | 1 | EA | 30000 | 30000 | 1972 | 30 | 7 | 2025 | 1000
Mechanical Systems | 6.11 | Steam condensate tank | 1 | EA | 40000 | 40000 | 2016 | 40 | 38 | 2056 | 1000
Mechanical Systems | 6.12 | Chilled water pumps | 2 | EA | 15000 | 30000 | - | 30 | 2 | 2020 | 1000
Mechanical Systems | 6.13 | Condenser water pumps | 2 | EA | 15000 | 30000 | - | 30 | 4 | 2022 | 1000
Mechanical Systems | 6.14 | Heating hot water pumps | 2 | EA | 15000 | 30000 | - | 30 | 6 | 2024 | 1000
Mechanical Systems | 6.15 | Heating hot water loop pumps | 2 | EA | 8000 | 16000 | - | 30 | 8 | 2026 | 533
Mechanical Systems | 6.16 | HVAC control system | 1 | LS | 40000 | 40000 | - | 30 | 10 | 2028 | 1333
Mechanical Systems | 6.17 | AHU-1 - west hallways and residences | 1 | EA | 100000 | 100000 | 2008 | 30 | 20 | 2038 | 3333
Mechanical Systems | 6.18 | AHU-2 - east hallways and residences | 1 | EA | 100000 | 100000 | 2008 | 30 | 20 | 2038 | 3333
Mechanical Systems | 6.19 | AHU-3 - B3 level | 1 | EA | 50000 | 50000 | 2007 | 30 | 19 | 2037 | 1667
Mechanical Systems | 6.2 | AHU-4 - swimming pool | 1 | EA | 75000 | 75000 | 2007 | 30 | 19 | 2037 | 2500
Mechanical Systems | 6.21 | Steam injection humidifiers | 2 | EA | 8000 | 16000 | 2000 | 25 | 7 | 2025 | 640
Mechanical Systems | 6.22 | Roof level exhaust fans | 1 | LS | 360000 | 360000 | - | 30 | 1 | 2019 | 12000
Mechanical Systems | 6.23 | Mechanical room exhaust fans | 1 | AL | 5000 | 5000 | - | 10 | 4 | 2022 | 500
Mechanical Systems | 6.24 | Valve replacement allowance | 1 | AL | 20000 | 20000 | - | 5 | 2 | 2020 | 4000
Mechanical Systems | 6.25 | East system water piping | 1 | LS | 800000 | 800000 | 1972 | 55 | 9 | 2027 | 14545
Mechanical Systems | 6.26 | West system water piping | 1 | LS | 700000 | 700000 | 1972 | 55 | 9 | 2027 | 12727
Mechanical Systems | 6.27 | Condenser water piping | 1 | LS | 60000 | 60000 | 1972 | 60 | 14 | 2032 | 1000
Mechanical Systems | 6.28 | Boiler room piping and valves | 1 | LS | 100000 | 100000 | 1972 | 65 | 19 | 2037 | 1538
Mechanical Systems | 6.29 | Boiler breeching | 1 | LS | 40000 | 40000 | 1972 | 45 | 3 | 2021 | 889
Mechanical Systems | 6.3 | Boiler flue | 1 | AL | 50000 | 50000 | 1972 | 50 | 5 | 2023 | 1000
Mechanical Systems | 6.31 | Boiler room ventilation fan | 1 | EA | 25000 | 25000 | - | 35 | 11 | 2029 | 714
Mechanical Systems | 6.32 | Residential fan coil units | 549 | EA | 5000 | 2745000 | 2014 | 30 | 26 | 2044 | 91500
Mechanical Systems | 6.33 | Common area fan coil units | 18 | EA | 5000 | 90000 | 2015 | 30 | 27 | 2045 | 3000
Mechanical Systems | 6.34 | AHU & pipe modifications for new system | 1 | LS | 50000 | 50000 | - | one_time_project | 3 | 2021 | $-
Mechanical Systems | 6.35 | Fuel oil tank | 1 | EA | 60000 | 60000 | - | 40 | 12 | 2030 | 1500
Mechanical Systems | 6.36 | Fuel oil transfer pumps and piping | 1 | LS | 25000 | 25000 | - | 30 | 10 | 2028 | 833
Mechanical Systems | 6.37 | Indoor air ducts | 1 | AL | 150000 | 150000 | 1972 | 65 | 19 | 2037 | 2308
Mechanical Systems | 6.38 | Air balancing | 1 | AL | 10000 | 10000 | - | 10 | 2 | 2020 | 1000
Mechanical Systems | 6.39 | Board room building HVAC | 1 | LS | 25000 | 25000 | 2000 | 25 | 7 | 2025 | 1000
Mechanical Systems | 6.4 | Elevator machine room HVAC | 2 | EA | 20000 | 40000 | 2009 | 20 | 11 | 2029 | 2000
Electrical Systems | 7.01 | High voltage switchgear | 1 | LS | 550000 | 550000 | 1972 | 60 | 14 | 2032 | 9167
Electrical Systems | 7.02 | Dry transformers | 1 | LS | 50000 | 50000 | 1972 | 60 | 14 | 2032 | 833
Electrical Systems | 7.03 | Common element load centers | 1 | LS | 250000 | 250000 | 1972 | 60 | 14 | 2032 | 4167
Electrical Systems | 7.04 | EV charging station equipment | 1 | LS | 30000 | 30000 | 2018 | 30 | 30 | 2048 | 1000
Electrical Systems | 7.05 | Common element wiring | 1 | LS | 250000 | 250000 | 1972 | 65 | 19 | 2037 | 3846
Electrical Systems | 7.06 | Emergency generator | 1 | EA | 120000 | 120000 | 2009 | 30 | 21 | 2039 | 4000
Electrical Systems | 7.07 | Transfer switches | 1 | LS | 35000 | 35000 | 2009 | 30 | 21 | 2039 | 1167
Electrical Systems | 7.08 | Interior lighting | 1 | AL | 25000 | 25000 | - | 30 | 12 | 2030 | 833
Electrical Systems | 7.09 | Garage lighting | 1 | AL | 15000 | 15000 | - | 30 | 10 | 2028 | 500
Electrical Systems | 7.1 | Exterior lighting | 1 | AL | 25000 | 25000 | - | 20 | 8 | 2026 | 1250
Electrical Systems | 7.11 | Electric system preventive maintenance | 1 | AL | 10000 | 10000 | - | 3 | 2 | 2020 | 3333
Electrical Systems | 7.12 | Electric unit heaters | 1 | AL | 5000 | 5000 | - | 10 | 8 | 2026 | 500
Plumbing Systems | 8.01 | Domestic water booster pumps | 1 | LS | 40000 | 40000 | 2007 | 25 | 14 | 2032 | 1600
Plumbing Systems | 8.02 | Domestic water circulating pump | 1 | EA | 5000 | 5000 | - | 15 | 8 | 2026 | 333
Plumbing Systems | 8.03 | Domestic water pressure tank | 1 | EA | 15000 | 15000 | 2007 | 35 | 24 | 2042 | 429
Plumbing Systems | 8.04 | Domestic hot water boilers & tank | 1 | LS | 180000 | 180000 | - | 30 | 3 | 2021 | 6000
Plumbing Systems | 8.05 | Water main | 1 | EA | 40000 | 40000 | 1972 | 65 | 19 | 2037 | 615
Plumbing Systems | 8.06 | Domestic water distribution pipes | 1 | LS | 1200000 | 1200000 | 1972 | 55 | 9 | 2027 | 21818
Plumbing Systems | 8.07 | Sanitary drain pipe risers | 1 | LS | 1200000 | 1200000 | 1972 | 60 | 14 | 2032 | 20000
Plumbing Systems | 8.08 | Storm water drain risers | 1 | LS | 200000 | 200000 | 1972 | 60 | 14 | 2032 | 3333
Plumbing Systems | 8.09 | Storm and sanitary drain main pipes | 1 | AL | 50000 | 50000 | 1972 | 10 | 6 | 2024 | 5000
Plumbing Systems | 8.1 | Condensate drain pipes | 1 | LS | 600000 | 600000 | 1972 | 55 | 9 | 2027 | 10909
Plumbing Systems | 8.11 | Dry valves for garage sprinklers | 1 | LS | 30000 | 30000 | 2017 | 15 | 14 | 2032 | 2000
Plumbing Systems | 8.12 | Garage sprinkler pipes | 1 | LS | 150000 | 150000 | 1972 | 55 | 9 | 2027 | 2727
Plumbing Systems | 8.13 | Gas pipe system | 1 | AL | 50000 | 50000 | 1972 | 70 | 24 | 2042 | 714
Miscellaneous Equipment | 9.01 | Elevator hoisting equipment and controls | 6 | EA | 180000 | 1080000 | 2009 | 40 | 31 | 2049 | 27000
Miscellaneous Equipment | 9.02 | Elevator door equipment | 6 | EA | 35000 | 210000 | 2009 | 20 | 11 | 2029 | 10500
Miscellaneous Equipment | 9.03 | Elevator cab redecoration allowance | 6 | EA | 15000 | 90000 | 2009 | 20 | 11 | 2029 | 4500
Miscellaneous Equipment | 9.04 | Fire alarm control panels | 1 | AL | 40000 | 40000 | 2017 | 20 | 19 | 2037 | 2000
Miscellaneous Equipment | 9.05 | Fire alarm system renovation | 1 | AL | 500000 | 500000 | 2017 | 40 | 39 | 2057 | 12500
Miscellaneous Equipment | 9.06 | Surveillance equipment | 1 | AL | 30000 | 30000 | - | 15 | 5 | 2023 | 2000
Miscellaneous Equipment | 9.07 | Trash compactors | 2 | EA | 25000 | 50000 | 1991 | 30 | 3 | 2021 | 1667
Miscellaneous Equipment | 9.08 | Entry access systems | 1 | LS | 40000 | 40000 | - | 30 | 8 | 2026 | 1333
Miscellaneous Equipment | 9.09 | Trash chutes | 2 | EA | 40000 | 80000 | - | 30 | 8 | 2026 | 2667
Interior Finishes and Furnishing | 10.01 | Hallway redecoration | 1 | AL | 500000 | 500000 | 2018 | 15 | 15 | 2033 | 33333
Interior Finishes and Furnishing | 10.02 | Elevator lobby redecoration | 1 | AL | 100000 | 100000 | 2018 | 15 | 15 | 2033 | 6667
Interior Finishes and Furnishing | 10.03 | Painting allowance | 1 | AL | 60000 | 60000 | 2018 | 7 | 7 | 2025 | 8571
Interior Finishes and Furnishing | 10.04 | Common area furnishing allowance | 1 | AL | 60000 | 60000 | 2018 | 15 | 15 | 2033 | 4000
Interior Finishes and Furnishing | 10.05 | Unit entry doors | 1 | AL | 250000 | 250000 | - | 50 | 32 | 2050 | 5000
Interior Finishes and Furnishing | 10.06 | Lobby renovation | 1 | AL | 120000 | 120000 | 2018 | 20 | 20 | 2038 | 6000
Interior Finishes and Furnishing | 10.07 | Management office redecoration | 1 | AL | 30000 | 30000 | - | 20 | 4 | 2022 | 1500
Interior Finishes and Furnishing | 10.08 | Service hallway redecoration | 1 | AL | 60000 | 60000 | - | 15 | 10 | 2028 | 4000
Interior Finishes and Furnishing | 10.09 | Locker and bath room renovation | 1 | AL | 80000 | 80000 | 2018 | 20 | 20 | 2038 | 4000
Interior Finishes and Furnishing | 10.1 | Sauna renovation | 1 | AL | 30000 | 30000 | 2018 | 15 | 15 | 2033 | 2000
Interior Finishes and Furnishing | 10.11 | Fitness center equipment replacement | 1 | AL | 15000 | 15000 | 2018 | 7 | 7 | 2025 | 2143
Interior Finishes and Furnishing | 10.12 | Fitness center redecoration | 1 | AL | 30000 | 30000 | 2018 | 15 | 15 | 2033 | 2000
Interior Finishes and Furnishing | 10.13 | Office equipment | 1 | AL | 5000 | 5000 | - | 5 | 1 | 2019 | 1000
Interior Finishes and Furnishing | 10.14 | Mailboxes | 1 | LS | 50000 | 50000 | - | 40 | 10 | 2028 | 1250